## Instructions
INSTRUCTIONS
Welcome to the Quick Start Kit – Menttor
How to use this file:
1) Start with the 'Charter 1-Pager' sheet and fill in the fields with your project.
2) Use the 'Kickoff Checklist' to prepare and run your project kickoff meeting.
3) Define roles in the 'RACI' sheets. You can use the example as a guide.
4) In each meeting, record decisions and actions in 'Executive Minutes'.
5) Map your next 60 days in '8-Week Roadmap'.
6) Review some concepts and definitions
Tip: Duplicate the sheets for different projects and use filters/colors for tracking.
Brand: Menttor
Clara Magin

## Charter 1-Pager
FIELD | CONTENT (FILL IN)
Project (Name)
Purpose (why does it exist?)
SMART objectives (3 max.)
Scope (what it includes)
Out of Scope (what it does NOT include)
Deliverables (measurable outputs)
Main milestones (tentative dates)
Key stakeholders
Roles (PM, Sponsor, Team)
Initial risks
Assumptions/Constraints
Budget (if applicable)
Kickoff Date
Next steps (1–2 weeks)

## Kickoff Checklist
STEP | DESCRIPTION | OWNER | STATUS (☐/✔) | COMMENTS
Define a clear objective for the meeting | In one sentence: what do we want to achieve today? |  | Ok
Share the agenda and materials in advance | Send agenda + context document 24h before |  | Pending
Quick team introduction | Name, role and objective of each participant
Align scope and out-of-scope | What we will and won't do in this project
Review key deliverables | List of expected outputs with success criteria
Agree on roles and responsibilities (RACI) | Who is Responsible (R), Approves (A), Consulted (C), Informed (I)
Identify initial risks and assumptions | Top 3 risks and assumptions that could affect timing/cost
Set milestones and next steps | Short-term dates and deliverables (1–2 weeks)
Define communication channels and rules | Tools, frequency, schedule, decisions and escalation
Confirm the follow-up date | Block the progress review in the calendar

## List (hidden)
Ok | Plan
Pending | In progress
Done

## RACI (Template)
Activity/Task | R (Responsible) | A (Approves) | C (Consulted) | I (Informed)
Define scope
Design solution
Build schedule
Approve budget
Sprint 1 execution
Progress review

## RACI (Example)
Activity/Task | R (Responsible) | A (Approves) | C (Consulted) | I (Informed)
Define scope | PM | Sponsor | Key Users | Team
Design solution | Technical Lead | PM | Key Users | PMO
Build schedule | PM | Sponsor | Technical Lead | PMO
Approve budget | Sponsor | Board | Finance | PMO
Sprint 1 execution | Dev Team | PM | QA/Support | Stakeholders
Progress review | PM | Sponsor | Team | Stakeholders

## Executive Minutes
Field | Content
Meeting
Date
Time
Participants
Objective
Points discussed
Decisions
Actions
Owner
Commitment Date
Risks/Blockers
Notes

## 8-Week Roadmap
Week | Milestone | Deliverables | Dependencies | Status (Plan/In progress/Done)
WEEK 1 |  |  |  | Plan
WEEK 2 |  |  |  | In progress
WEEK 3 |  |  |  | Done
WEEK 4
WEEK 5
WEEK 6
WEEK 7
WEEK 8

## Definitions
TERM | DEFINITION
Project Charter | Document that formally authorizes a project and defines its scope, objectives and owners.
SMART Objective | A specific, measurable, achievable, relevant and time-bound goal.
Deliverable | A tangible product, service or result to be delivered in the project.
Stakeholder | A person or group interested in or affected by the project.
PM (Project Manager) | Responsible for planning, executing and closing the project.
Kickoff | Initial meeting to present the project and align expectations.
Milestone | A key point or important achievement within the project schedule.
RACI | A matrix that defines roles: Responsible, Approver, Consulted and Informed.
SPRINT | A short, defined period to complete tasks in agile methodologies.
ROADMAP | A visual plan showing the project's strategy and phases over time.